## Sheet1
Milestone: | Expected Completion Date: | Actual Date of Completion: | Reason:
Design | 03.01.2021 | 4.13.21
Implementation Phase 1 | 03.29.2021 | N/A | Behind schedule due to poor initial planning and responsibilities to other projects.
Implementation Phase 2 | 04.24.2021 | N/A | Implementation Phase 1 is incomplete.